MOR Executive Status Report

Morning Operations Review | Jun 9, 2026

Scope assumption: No Jira project key was provided, so this report covers all 15 Jira software projects visible in Cattron Jira: BWI, CBMCU, CDA, CMA, EE6, EX, IRMCU, IROCU, LEARNJIRA, MBA, SCI, SO, SRC, STKJ, XBMCU. Sample/training projects may skew totals.

# 1. Executive Summary

Overall project health: 🔴 Red

Why Red: 175 open issues, 115 open defects, 49 unassigned tickets, several overdue items, and only 1 issue completed in the last 7 days.

Key achievement since previous update: CDA-78 completed today - "Hex file generation proceeds even when SOAL file contains errors."

Major risk: Defects represent approximately 66% of open work.

Major risk: Multiple overdue CattronLink/CANopen items remain unresolved.

Ownership risk: 49 open issues are unassigned.

Planning visibility risk: Sprint, story point, velocity, and capacity fields are not populated or exposed in the Jira data.

| Executive KPI | Current Value | Status |
| --- | --- | --- |
| Total open issues | 175 | 🔴 Red |
| Open defects | 115 | 🔴 Red |
| Completed this week | 1 | 🔴 Red |
| Completed today | 1 | 🟡 Amber |
| Explicitly blocked tickets | 0 | 🟢 Green |
| Unassigned open issues | 49 | 🔴 Red |

# 2. Work Completed Since Last Update

| Group | Issue | Summary | Assignee | Completed |
| --- | --- | --- | --- | --- |
| CDA / CattronLink Desktop App | CDA-78 | Hex file generation proceeds even when SOAL file contains errors | Duyet Vo | Jun 9, 2026 |

# 3. Work In Progress

Active/WIP status-category issues: 100

Percent complete is generally unavailable; one item shows 100% progress but remains open.

Estimated completion dates are based on Jira due dates where available.

| Issue | Summary | Assignee | Status | Est. completion | % complete | Risk |
| --- | --- | --- | --- | --- | --- | --- |
| CDA-96 | SRDO Creation Tool lacks CANopen Safety COB-ID validation | Sambangi Sankararao | TESTING/VALIDATION | Overdue May 19 | N/A | 🔴 Highest priority, overdue |
| CDA-97 | SRDO Refresh Time fails to persist | Sambangi Sankararao | TESTING/VALIDATION | Overdue May 27 | N/A | 🔴 Overdue |
| CDA-100 | Bad Variable indexing | Sambangi Sankararao | TESTING/VALIDATION | Overdue May 28 | N/A | 🔴 Overdue |
| CDA-103 | Generate CANopen Safety objects | Sambangi Sankararao | TESTING/VALIDATION | Overdue Jun 3 | N/A | 🟡 Overdue |
| CDA-110 | CANopen transmit/receive selection not functioning | Sambangi Sankararao | In Progress | Due Jun 11 | N/A | 🟡 Near-term due |
| CDA-65 | OCU failed to write configuration | Duyet Vo | TESTING/VALIDATION | N/A | N/A | 🔴 Highest priority, stale |
| IROCU-7 | IR SubGHz Radio SDK issue with Silicon REV C | Duyet Vo | TESTING/VALIDATION | N/A | N/A | 🔴 Highest priority, stale |
| CDA-101 | Disconnect prompt on first OCU power-up | Nagesh Prajapati | In Progress | N/A | N/A | 🟡 Active defect |
| CDA-75 | Export/import SOAL user variable | Sambangi Sankararao | In Progress | Overdue May 8 | N/A | 🔴 Overdue |
| SCI-23 | SOAL application sample interface document | Joel Kish | In Progress | N/A | 100% | 🟡 Progress complete but not closed |

# 4. Blocked Issues

| Blocked count | Details | Required action |
| --- | --- | --- |
| 0 | No issues explicitly found in Blocked status or with blocked/blocker/impediment labels. | Confirm teams are using blocker labels/status consistently. |

Note: Absence of explicit blocked tickets does not remove delivery risk; overdue/stale WIP indicates latent blockers may not be labeled.

# 5. Sprint Status

| Metric | Status |
| --- | --- |
| Sprint goal | Not available in exposed Jira fields |
| Story points completed | Not available |
| Story points remaining | Not available |
| Burndown summary | Not available |
| Predicted sprint completion | 🔴 At risk / cannot validate due missing sprint data |

# 6. KPI Dashboard

| KPI | Value | Indicator |
| --- | --- | --- |
| Total open issues | 175 | 🔴 |
| Open defects | 115 | 🔴 |
| Issues completed this week | 1 | 🔴 |
| Issues completed today | 1 | 🟡 |
| Blocked ticket count | 0 | 🟢 |
| Reopened ticket count | 0 | 🟢 |
| Unassigned open issues | 49 | 🔴 |
| Story points completed vs planned | Not available | 🟡 |
| Sprint velocity | Not available | 🟡 |
| Cycle time | Not available | 🟡 |
| Lead time for completed issue | ~47 days | 🔴 |
| Defect leakage rate | Not available | 🟡 |

# 7. Team Performance

| Assignee | Open workload | Status |
| --- | --- | --- |
| Duyet Vo | 41 | 🔴 Overloaded |
| Sambangi Sankararao | 21 | 🔴 Overloaded |
| michael | 14 | 🟡 High |
| Khang Le | 13 | 🟡 High |
| Nagesh Prajapati | 13 | 🟡 High |
| Kinjalkumar Vaghela | 7 | 🟢 Manageable |
| Avinash Patel | 7 | 🟢 Manageable |
| Unassigned | 49 | 🔴 Ownership gap |

Top contributor this period: Duyet Vo - 1 completed issue.

# 8. Upcoming Milestones

| Window | Deliverables / due items | Risk |
| --- | --- | --- |
| Next 7 days | CDA-110 due Jun 11 | 🟡 Needs close tracking |
| Overdue carryover | CDA-96, CDA-97, CDA-100, CDA-103, CDA-75, CDA-77, CDA-86 | 🔴 Immediate recovery needed |
| 14 / 30 days | No reliable milestone data exposed beyond due dates | 🟡 Planning gap |

# 9. Actions Required

| Priority | Action | Owner / Decision Needed |
| --- | --- | --- |
| 🔴 | Confirm whether this MOR should include all visible Jira projects or a specific Jira project key. | Management |
| 🔴 | Review overdue CDA/CANopen items today and assign recovery owners. | Engineering / PM |
| 🔴 | Triage 49 unassigned tickets; assign or close stale/sample items. | Project leads |
| 🟡 | Populate sprint, story point, due date, and fix version fields for delivery tracking. | Scrum masters / PM |
| 🟡 | Prioritize top defects in CDA, CBMCU, and CANopen workstreams before adding new scope. | Product / Engineering leadership |